## Features
Fields
Feature Id
Game State | What state the game is in for each area
Area
Feature | Name of the feature
Description | Sufficient text to fully explain the how the feature works
FEATURES
Feature Id | Game State | Area | Features | Description
1 | Loading Screen | Function | Load data | Loads game assets
2 | Loading Screen | Assets | Loading text/background | Loading screen has a background and loading screen text
3 | Main Menu | Function | Buttons | Start game, Exit Game buttons to start or exit the game
4 | Main Menu | Function | Options | Main Menu has Option screen to change audio settings
5 | Main Menu | Assets | Background | Background Art/Music playing on loop
6 | Game | Assets | Background music | Background music is playing on loop
7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
9 | Game | Camera | Top down camera | Camera view is top down focusing on the player but is clamped to screen
10 | Game | Camera | Screen shake | Camera has screen shaking for for big damage taken
11 | Game | UI | Pause Menu | Pause menu pauses gameplay and has buttons for resuming gameplay and quitting
12 | Game | UI | Pause Menu Audio controls | Lowering and raising of the audio can be done through pause menu
13 | Game | UI | HUD | There is a HUD that shows health, ammo, and current weapon
14 | Game | UI | Death Sequence | When the player dies, there is a transition to the death screen which allows the player to restart or go back to main menu
15 | Game | UI | Map transition sequence | When a level is completed there is a transition sequence to the next level
16 | Game | UI | Victory sequence | When the full game is beaten, a vicotry sequence begins which then allows the player to restart or go back to main menu
17 | Game | Actors | Physics | Physics like actor radius is data driven and says what the actor will collide with
18 | Game | Actors | Weapons | Game keeps track of current weapon and uses the weapon definitions to know the stats
19 | Game | Actors | Model/animations | Actors model and animations are data driven with walking and death
20 | Game | Player | Player Character | The Player character is derived from actor with a player controller
21 | Game | Player Controller | Movement | Player moves with WASD or controller left joystick
22 | Game | Player Controller | Shooting | Player shoots with left mouse button or controller right button
23 | Game | Player Controller | Aiming | Player aims with mouse or controller right joystick
24 | Game | Player Controller | Dodging | Player can dodge with space key or controller B button
25 | Game | Player Controller | Changing weapons | Player can change weapons with Q/E keys or controller Y button
26 | Game | Player Controller | Interact/pick up loot | Player can pick up weapons/interact with F key or controller A button
27 | Game | Enemies | Enemy characters | Enemies are actors that may be data driven. They have on hit and on death effects to drop loot
28 | Game | Enemy Controller | Enemy AI Controller | Enemies have a data driven controller where they will wander until the player is spotted before chasing and shooting
29 | Game | Enemy | Boss | Bosses are enemies with a heavier data driven controller for larger attack animations and on hit effects
30 | Game | Actors | Loot | Loot can be dropped from enemies for example weapons, and can be picked up
31 | Game | Map | Map editor | Maps are data driven and use an image with pixels determining what's on the terrain
32 | Game | Map | Map generation | Maps are room based and lock all doors on player entry until enemies are cleares
33 | Game | Map | Map makeup | Maps are tile based with tile definitions determining what/who they block or not block
34 | Game | World | Levels | The game is made up of multiple maps which are each a level
35 | Game | Player | Player character weapon | The player weapon faces the direction that the player is aiming. The weapon makes a circular motion around the character and isn't fully connected to the body
36 | Polish | Polish | Polish | Polish
37 | Game | Protogame | Protogame | Create Protogame as starting point

## Milestones
Milestones | Dates
Milestone 1 | 2020-06-15
Milestone 2 | 2020-06-29
Milestone 3 | 2020-07-13
Final Deliverable | 2020-07-21
Milestones | Feature ID | Game State | Area | Features | Description
Final Deliverable | 36 | Polish | Polish | Polish | Polish
Milestone 1 | 1 | Loading Screen | Function | Load data | Loads game assets
Milestone 1 | 2 | Loading Screen | Assets | Loading text/background | Loading screen has a background and loading screen text
Milestone 1 | 3 | Main Menu | Function | Buttons | Start game, Exit Game buttons to start or exit the game
Milestone 1 | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
Milestone 1 | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
Milestone 1 | 9 | Game | Camera | Top down camera | Camera view is top down focusing on the player but is clamped to screen
Milestone 1 | 17 | Game | Actors | Physics | Physics like actor radius is data driven and says what the actor will collide with
Milestone 1 | 18 | Game | Actors | Weapons | Game keeps track of current weapon and uses the weapon definitions to know the stats
Milestone 1 | 19 | Game | Actors | Model/animations | Actors model and animations are data driven with walking and death
Milestone 1 | 20 | Game | Player | Player Character | The Player character is derived from actor with a player controller
Milestone 1 | 21 | Game | Player Controller | Movement | Player moves with WASD or controller left joystick
Milestone 1 | 22 | Game | Player Controller | Shooting | Player shoots with left mouse button or controller right button
Milestone 1 | 23 | Game | Player Controller | Aiming | Player aims with mouse or controller right joystick
Milestone 2 | 10 | Game | Camera | Screen shake | Camera has screen shaking for for big damage taken
Milestone 2 | 11 | Game | UI | Pause Menu | Pause menu pauses gameplay and has buttons for resuming gameplay and quitting
Milestone 2 | 13 | Game | UI | HUD | There is a HUD that shows health, ammo, and current weapon
Milestone 2 | 24 | Game | Player Controller | Dodging | Player can dodge with space key or controller B button
Milestone 2 | 25 | Game | Player Controller | Changing weapons | Player can change weapons with Q/E keys or controller Y button
Milestone 2 | 26 | Game | Player Controller | Interact/pick up loot | Player can pick up weapons/interact with F key or controller A button
Milestone 2 | 27 | Game | Enemies | Enemy characters | Enemies are actors that may be data driven. They have on hit and on death effects to drop loot
Milestone 2 | 31 | Game | Map | Map editor | Maps are data driven and use an image with pixels determining what's on the terrain
Milestone 2 | 32 | Game | Map | Map generation | Maps are room based and lock all doors on player entry until enemies are cleares
Milestone 2 | 33 | Game | Map | Map makeup | Maps are tile based with tile definitions determining what/who they block or not block
Milestone 2 | 34 | Game | World | Levels | The game is made up of multiple maps which are each a level
Milestone 2 | 35 | Game | Player | Player character weapon | The player weapon faces the direction that the player is aiming. The weapon makes a circular motion around the character and isn't fully connected to the body
Milestone 3 | 4 | Main Menu | Function | Options | Main Menu has Option screen to change audio settings
Milestone 3 | 5 | Main Menu | Assets | Background | Background Art/Music playing on loop
Milestone 3 | 6 | Game | Assets | Background music | Background music is playing on loop
Milestone 3 | 12 | Game | UI | Pause Menu Audio controls | Lowering and raising of the audio can be done through pause menu
Milestone 3 | 14 | Game | UI | Death Sequence | When the player dies, there is a transition to the death screen which allows the player to restart or go back to main menu
Milestone 3 | 15 | Game | UI | Map transition sequence | When a level is completed there is a transition sequence to the next level
Milestone 3 | 16 | Game | UI | Victory sequence | When the full game is beaten, a vicotry sequence begins which then allows the player to restart or go back to main menu
Milestone 3 | 28 | Game | Enemy Controller | Enemy AI Controller | Enemies have a data driven controller where they will wander until the player is spotted before chasing and shooting
Milestone 3 | 29 | Game | Enemy | Boss | Bosses are enemies with a heavier data driven controller for larger attack animations and on hit effects
Milestone 3 | 30 | Game | Actors | Loot | Loot can be dropped from enemies for example weapons, and can be picked up

## Backlog
Status Codes | Status meaning |  |  | Status Tags
O | Not Started |  |  | * | Not originally planned
/ | In Progress |  |  | ! | Highest priority
X | Complete
< | Sent to backlog
> | Carried to next sprint
D | Deleted
Task ID | Status | Estimate | Actual | Task | Feature ID | Game State | Area | Features | Description
1 | X | 1 | 1 | Implement loading state and loading functions | 1 | Loading Screen | Function | Load data | Loads game assets
2 | > | 1 | 0 | Implement loading screen text and background | 2 | Loading Screen | Assets | Loading text/background | Loading screen has a background and loading screen text
3 | X | 0.5 | 1 | Add Attract Screen functionality (space or lmb to start game) | 3 | Main Menu | Function | Buttons | Start game, Exit Game buttons to start or exit the game
4 | 0 | 1 | 0 | Implement visuals for the buttons | 3 | Main Menu | Function | Buttons | Start game, Exit Game buttons to start or exit the game
5 | 0 | 1 | 0 | Create Options menu with ability to set Audio volume | 4 | Main Menu | Function | Options | Main Menu has Option screen to change audio settings
6 | 0 | 1 | 0 | Find/Add background art/music to Main menu | 5 | Main Menu | Assets | Background | Background Art/Music playing on loop
7 | 0 | 1 | 0 | Find/Add background music for gameplay | 6 | Game | Assets | Background music | Background music is playing on loop
8 | X | 1.5 | 2 | Create Weapon Definition | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
9 | X | 1 | 1 | Implement shooting using weapon definition | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
10 | 0 | 1 | 0 | Implement VFX/SFX activation for weapons | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
11 | X | 1 | 0.5 | Integrate Weapons with bullets | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
12 | X | 1.5 | 0.5 | Integrate Weapon with actors | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
13 | X | 1 | 0.5 | Find/implement first 2 weapon assets (pistol/shotgun) | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
14 | X | 1.5 | 0.5 | Find/implement machine gun and flamethrower | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
15 | X | 1 | 0.5 | Find/implement laser gun | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
16 | X | 1 | 0.5 | Find/implement rocket launcher | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
17 | X | 1.5 | 1.5 | Create Bullet Definition | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
18 | X | 1 | 1 | Implement bullet collisions | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
19 | X | 1 | 0.5 | Find/implement basic bullet asset | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
20 | 0 | 2 | 0 | Implement rest of bullet assets | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
21 | X | 1 | 1 | Create camera to follow player | 9 | Game | Camera | Top down camera | Camera view is top down focusing on the player but is clamped to screen
22 | X | 0.5 | 0.5 | Clamp camera to map dimensions | 9 | Game | Camera | Top down camera | Camera view is top down focusing on the player but is clamped to screen
23 | X | 1 | 1 | Implement screen shake | 10 | Game | Camera | Screen shake | Camera has screen shaking for for big damage taken
24 | 0 | 2 | 0 | Implement basic pause buttons, darken screen, stop time in game, and remove game controls | 11 | Game | UI | Pause Menu | Pause menu pauses gameplay and has buttons for resuming gameplay and quitting
25 | < | 2 | 0 | Implement pause menu audio controls | 12 | Game | UI | Pause Menu Audio controls | Lowering and raising of the audio can be done through pause menu
26 | / | 1 | 1 | Implement a HUD that shows health, ammo, and current weapon | 13 | Game | UI | HUD | There is a HUD that shows health, ammo, and current weapon
27 | 0 | 2 | 0 | Create a transition for death where the screen fades to black and options to restart or go to main menu appear | 14 | Game | UI | Death Sequence | When the player dies, there is a transition to the death screen which allows the player to restart or go back to main menu
28 | 0 | 1.5 | 0 | Create a transition to fade in/out for between maps | 15 | Game | UI | Map transition sequence | When a level is completed there is a transition sequence to the next level
29 | 0 | 1 | 0 | Create victory state transition with restart/ go to main menu buttons | 16 | Game | UI | Victory sequence | When the full game is beaten, a vicotry sequence begins which then allows the player to restart or go back to main menu
30 | X | 1 | 1 | Implement Actor physics with collisions of enemies and obstacles | 17 | Game | Actors | Physics | Physics like actor radius is data driven and says what the actor will collide with
31 | X | 1 | 1.5 | Have weapons face actor direction moving in a circular motion around player radius | 18 | Game | Actors | Weapons | Game keeps track of current weapon and uses the weapon definitions to know the stats
32 | X | 1 | 0.5 | Have weapons behind player at top of screen and in front of player at bottom of screen | 18 | Game | Actors | Weapons | Game keeps track of current weapon and uses the weapon definitions to know the stats
33 | D | 1.5 | 0 | Implement Actor Definition (Done in Testgame2D base) | 19 | Game | Actors | Model/animations | Actors model and animations are data driven with walking and death
34 | 0 | 1.5 | 0 | Implement Actor rendering and class | 19 | Game | Actors | Model/animations | Actors model and animations are data driven with walking and death
35 | 0 | 1.5 | 0 | Create player character class (might not be necessary) | 20 | Game | Player | Player Character | The Player character is derived from actor with a player controller
36 | 0 | 1 | 0 | Create controller class | 21 | Game | Player Controller | Movement | Player moves with WASD or controller left joystick
37 | X | 1 | 0.25 | Add movement controls (WASD) | 21 | Game | Player Controller | Movement | Player moves with WASD or controller left joystick
38 | X | 1 | 0.25 | Add shooting controls (LMB) | 22 | Game | Player Controller | Shooting | Player shoots with left mouse button or controller right button
39 | X | 1 | 0.25 | Add aiming controls (Mouse) | 23 | Game | Player Controller | Aiming | Player aims with mouse or controller right joystick
40 | X | 1 | 1 | Add dodging to controller class | 24 | Game | Player Controller | Dodging | Player can dodge with space key or controller B button
41 | X | 1 | 1 | Add changing weapons to controller class | 25 | Game | Player Controller | Changing weapons | Player can change weapons with Q/E keys or controller Y button
42 | X | 1 | 1 | Add interacting/picking up loot to controller | 26 | Game | Player Controller | Interact/pick up loot | Player can pick up weapons/interact with F key or controller A button
43 | 0 | 2 | 0 | Create Enemy definitions (could use same as player with a different controller specified) | 27 | Game | Enemies | Enemy characters | Enemies are actors that may be data driven. They have on hit and on death effects to drop loot
44 | X | 2 | 0.5 | Create simple enemy controller to run at player and shoot | 28 | Game | Enemy Controller | Enemy AI Controller | Enemies have a data driven controller where they will wander until the player is spotted before chasing and shooting
45 | 0 | 3 | 0 | Create smart AI to avoid walls | 28 | Game | Enemy Controller | Enemy AI Controller | Enemies have a data driven controller where they will wander until the player is spotted before chasing and shooting
46 | X | 3 | 3.5 | Create first boss using enemies as a base. They will be enemies with bigger hitbox and multiple attacks | 29 | Game | Enemy | Boss | Bosses are enemies with a heavier data driven controller for larger attack animations and on hit effects
47 | 0 | 2 | 0 | Create second boss following same pattern as first boss | 29 | Game | Enemy | Boss | Bosses are enemies with a heavier data driven controller for larger attack animations and on hit effects
48 | 0 | 2 | 0 | Create third boss | 29 | Game | Enemy | Boss | Bosses are enemies with a heavier data driven controller for larger attack animations and on hit effects
49 | X | 1 | 1 | Create loot capabilities in Actor definition | 30 | Game | Actors | Loot | Loot can be dropped from enemies for example weapons, and can be picked up
50 | X | 1 | 0.5 | Build Datadriven map from image file | 31 | Game | Map | Map editor | Maps are data driven and use an image with pixels determining what's on the terrain
51 | X | 2 | 2 | Implement enemy spawning | 32 | Game | Map | Map generation | Maps are room based and lock all doors on player entry until enemies are cleares
52 | D | 2 | 0 | Build tile definitions (done in Testgame2D base) | 33 | Game | Map | Map makeup | Maps are tile based with tile definitions determining what/who they block or not block
53 | D | 3 | 0 | Build map definition (done in Testgame2D base) | 33 | Game | Map | Map makeup | Maps are tile based with tile definitions determining what/who they block or not block
54 | X | 5 | 2.5 | Integrate map with actors and check collisions | 33 | Game | Map | Map makeup | Maps are tile based with tile definitions determining what/who they block or not block
55 | > | 2 | 0 | Create multiple map integration | 34 | Game | World | Levels | The game is made up of multiple maps which are each a level
56 | X | 2 | 1 | Create first map | 34 | Game | World | Levels | The game is made up of multiple maps which are each a level
57 | 0 | 2 | 0 | Create second map | 34 | Game | World | Levels | The game is made up of multiple maps which are each a level
58 | 0 | 2 | 0 | Create third map | 34 | Game | World | Levels | The game is made up of multiple maps which are each a level
59 | D | X | 0 | DUPLICATE | 35 | Game | Player | Player character weapon | The player weapon faces the direction that the player is aiming. The weapon makes a circular motion around the character and isn't fully connected to the body
60 | 0 | 10 | 0 | Polish | 36 | Polish | Polish | Polish | Polish
61 | *X | 1 | 0.5 | Create Prototype player | 20 | Game | Player | Player Character | The Player character is derived from actor with a player controller
62 | *X | 1 | 1 | Create prototype gun | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
63 | *X | 1 | 1 | Create Prototype bullets/firing | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
64 | *X | 1 | 1 | Create simple Enemy character with functions to shoot | 27 | Game | Enemies | Enemy characters | Enemies are actors that may be data driven. They have on hit and on death effects to drop loot
65 | *X | 2 | 4 | Create Protogame as starting place | 37 | Game | Protogame | Protogame | Create Protogame as starting point
66 | *X | 2 | 3 | Implement Incursion style map and tank (doesn't shoot) | 37 | Game | Protogame | Protogame | Create Protogame as starting point
67 | *X | 4 | 5 | Refactor Testgame2D to be used as a base project | 37 | Game | Protogame | Protogame | Create Protogame as starting point
68 | *X | 2 | 4 | Clean up weapon rendering | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
69 | */ | 2 | 3 | Find a different sprite sheet/ remove hands from current sprite sheet | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
70 | 0 | 2 | 0 | Implement Room Locking | 32 | Game | Map | Map generation | Maps are room based and lock all doors on player entry until enemies are cleares
71 | *0 | 0.5 | 0 | Fix Dodge bug where the player reaches light speed | 24 | Game | Player Controller | Dodging | Player can dodge with space key or controller B button
72 | *0 | 1 | 0 | Implement Ammo | 13 | Game | UI | HUD | There is a HUD that shows health, ammo, and current weapon
73 | *0 | 0.5 | 0 | Fix Fire Rate bug where sometimes multiple shots are fired | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
74 | *0 | 0.5 | 0 | Fix Quit bug where clicking exit doesn't quit | 3 | Main Menu | Function | Buttons | Start game, Exit Game buttons to start or exit the game
75 | */ | 6 | 3 | Work with Dhi to implement art assets | 36 | Polish | Polish | Polish | Polish
|  | 121.5 | 57.75

## Sprints
Status Codes | Status meaning |  |  | Status Tags
O | Not Started |  |  | * | Not originally planned
/ | In Progress |  |  | ! | Highest priority
X | Complete
< | Sent to backlog
> | Carried to next sprint
D | Deleted
Current Sprint
Milestone 1: 6/15/2020
Task ID | Status | Estimate | Actual | Task | Feature ID | Game State | Area | Features | Description
67 | *X | 4 | 5 | Refactor Testgame2D to be used as a base project | 37 | Game | Protogame | Protogame | Create Protogame as starting point
65 | *X | 2 | 4 | Create Protogame as starting place | 37 | Game | Protogame | Protogame | Create Protogame as starting point
66 | *X | 2 | 3 | Implement Incursion style map and tank (doesn't shoot) | 37 | Game | Protogame | Protogame | Create Protogame as starting point
64 | *X | 1 | 1 | Create simple Enemy character with functions to shoot | 27 | Game | Enemies | Enemy characters | Enemies are actors that may be data driven. They have on hit and on death effects to drop loot
61 | *X | 1 | 0.5 | Create Prototype player | 20 | Game | Player | Player Character | The Player character is derived from actor with a player controller
62 | *X | 1 | 1 | Create prototype gun | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
63 | *X | 1 | 1 | Create Prototype bullets/firing | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
1 | X | 1 | 1 | Implement loading state and loading functions | 1 | Loading Screen | Function | Load data | Loads game assets
3 | X | 0.5 | 1 | Add Attract Screen functionality (space or lmb to start game) | 3 | Main Menu | Function | Buttons | Start game, Exit Game buttons to start or exit the game
11 | X | 1 | 0.5 | Integrate Weapons with bullets | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
12 | X | 1.5 | 0.5 | Integrate Weapon with actors | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
18 | X | 1 | 1 | Implement bullet collisions | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
19 | X | 1 | 0.5 | Find/implement basic bullet asset | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
21 | X | 1 | 1 | Create camera to follow player | 9 | Game | Camera | Top down camera | Camera view is top down focusing on the player but is clamped to screen
22 | X | 0.5 | 0.5 | Clamp camera to map dimensions | 9 | Game | Camera | Top down camera | Camera view is top down focusing on the player but is clamped to screen
30 | X | 1 | 1 | Implement Actor physics with collisions of enemies and obstacles | 17 | Game | Actors | Physics | Physics like actor radius is data driven and says what the actor will collide with
31 | X | 1 | 1.5 | Have weapons face actor direction moving in a circular motion around player radius | 18 | Game | Actors | Weapons | Game keeps track of current weapon and uses the weapon definitions to know the stats
32 | X | 1 | 0.5 | Have weapons behind player at top of screen and in front of player at bottom of screen | 18 | Game | Actors | Weapons | Game keeps track of current weapon and uses the weapon definitions to know the stats
37 | X | 1 | 0.25 | Add movement controls (WASD) | 21 | Game | Player Controller | Movement | Player moves with WASD or controller left joystick
38 | X | 1 | 0.25 | Add shooting controls (LMB) | 22 | Game | Player Controller | Shooting | Player shoots with left mouse button or controller right button
39 | X | 1 | 0.25 | Add aiming controls (Mouse) | 23 | Game | Player Controller | Aiming | Player aims with mouse or controller right joystick
44 | X | 2 | 0.5 | Create simple enemy controller to run at player and shoot | 28 | Game | Enemy Controller | Enemy AI Controller | Enemies have a data driven controller where they will wander until the player is spotted before chasing and shooting
54 | X | 5 | 2.5 | Integrate map with actors and check collisions | 33 | Game | Map | Map makeup | Maps are tile based with tile definitions determining what/who they block or not block
|  | 32.5 | 28.25
| Initial Estimate | 27
| End Estimate | 32.5
| Removed | 6.5
| Estimated/Actual diff | 4.25
| Unplanned hours | 12
Removed From Milestone 1
8 | X | 1.5 | 2 | Create Weapon Definition | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
9 | X | 1 | 1 | Implement shooting using weapon definition | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
17 | X | 1.5 | 1.5 | Create Bullet Definition | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
13 | X | 1 | 0.5 | Find/implement first 2 weapon assets (pistol/shotgun) | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
33 | D | 1.5 | 0 | Implement Actor Definition (Done in Testgame2D base) | 19 | Game | Actors | Model/animations | Actors model and animations are data driven with walking and death
Milestone 2 | 2020-06-29
Task ID | Status | Estimate | Actual | Task | Feature ID | Game State | Area | Features | Description
8 | X | 1.5 | 2 | Create Weapon Definition | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
9 | X | 1 | 1 | Implement shooting using weapon definition | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
13 | X | 1 | 0.5 | Find/implement first 2 weapon assets (pistol/shotgun) | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
17 | X | 1.5 | 1.5 | Create Bullet Definition | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
23 | X | 1 | 1 | Implement screen shake | 10 | Game | Camera | Screen shake | Camera has screen shaking for for big damage taken
25 | < | 2 | 0 | Implement pause menu audio controls | 12 | Game | UI | Pause Menu Audio controls | Lowering and raising of the audio can be done through pause menu
26 | / | 1 | 1 | Implement a HUD that shows health, ammo, and current weapon | 13 | Game | UI | HUD | There is a HUD that shows health, ammo, and current weapon
40 | X | 1 | 1 | Add dodging to controller class | 24 | Game | Player Controller | Dodging | Player can dodge with space key or controller B button
41 | X | 1 | 1 | Add changing weapons to controller class | 25 | Game | Player Controller | Changing weapons | Player can change weapons with Q/E keys or controller Y button
42 | X | 1 | 1 | Add interacting/picking up loot to controller | 26 | Game | Player Controller | Interact/pick up loot | Player can pick up weapons/interact with F key or controller A button
50 | X | 1 | 0.5 | Build Datadriven map from image file | 31 | Game | Map | Map editor | Maps are data driven and use an image with pixels determining what's on the terrain
51 | X | 2 | 2 | Implement enemy spawning | 32 | Game | Map | Map generation | Maps are room based and lock all doors on player entry until enemies are cleares
55 | > | 2 | 0 | Create multiple map integration | 34 | Game | World | Levels | The game is made up of multiple maps which are each a level
56 | X | 2 | 1 | Create first map | 34 | Game | World | Levels | The game is made up of multiple maps which are each a level
2 | > | 1 | 0 | Implement loading screen text and background | 2 | Loading Screen | Assets | Loading text/background | Loading screen has a background and loading screen text
14 | X | 1.5 | 0.5 | Find/implement machine gun and flamethrower | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
15 | X | 1 | 0.5 | Find/implement laser gun | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
16 | X | 1 | 0.5 | Find/implement rocket launcher | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
46 | X | 3 | 3.5 | Create first boss using enemies as a base. They will be enemies with bigger hitbox and multiple attacks | 29 | Game | Enemy | Boss | Bosses are enemies with a heavier data driven controller for larger attack animations and on hit effects
49 | X | 1 | 1 | Create loot capabilities in Actor definition | 30 | Game | Actors | Loot | Loot can be dropped from enemies for example weapons, and can be picked up
68 | *X | 2 | 4 | Clean up weapon rendering | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
69 | */ | 2 | 3 | Find a different sprite sheet/ remove hands from current sprite sheet | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
75 | */ | 6 | 3 | Work with Dhi to implement art assets | 36 | Polish | Polish | Polish | Polish
|  | 37.5 | 29.5
Milestone 3 | 2020-07-13
Task ID | Status | Estimate | Actual | Task | Feature ID | Game State | Area | Features | Description
4 | 0 | 1 | 0 | Implement visuals for the buttons | 3 | Main Menu | Function | Buttons | Start game, Exit Game buttons to start or exit the game
6 | 0 | 1 | 0 | Find/Add background art/music to Main menu | 5 | Main Menu | Assets | Background | Background Art/Music playing on loop
7 | 0 | 1 | 0 | Find/Add background music for gameplay | 6 | Game | Assets | Background music | Background music is playing on loop
10 | 0 | 1 | 0 | Implement VFX/SFX activation for weapons | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
20 | 0 | 2 | 0 | Implement rest of bullet assets | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
24 | 0 | 2 | 0 | Implement basic pause buttons, darken screen, stop time in game, and remove game controls | 11 | Game | UI | Pause Menu | Pause menu pauses gameplay and has buttons for resuming gameplay and quitting
27 | 0 | 2 | 0 | Create a transition for death where the screen fades to black and options to restart or go to main menu appear | 14 | Game | UI | Death Sequence | When the player dies, there is a transition to the death screen which allows the player to restart or go back to main menu
28 | 0 | 1.5 | 0 | Create a transition to fade in/out for between maps | 15 | Game | UI | Map transition sequence | When a level is completed there is a transition sequence to the next level
27 | 0 | 2 | 0 | Create a transition for death where the screen fades to black and options to restart or go to main menu appear | 14 | Game | UI | Death Sequence | When the player dies, there is a transition to the death screen which allows the player to restart or go back to main menu
28 | 0 | 1.5 | 0 | Create a transition to fade in/out for between maps | 15 | Game | UI | Map transition sequence | When a level is completed there is a transition sequence to the next level
29 | 0 | 1 | 0 | Create victory state transition with restart/ go to main menu buttons | 16 | Game | UI | Victory sequence | When the full game is beaten, a vicotry sequence begins which then allows the player to restart or go back to main menu
47 | 0 | 2 | 0 | Create second boss following same pattern as first boss | 29 | Game | Enemy | Boss | Bosses are enemies with a heavier data driven controller for larger attack animations and on hit effects
48 | 0 | 2 | 0 | Create third boss | 29 | Game | Enemy | Boss | Bosses are enemies with a heavier data driven controller for larger attack animations and on hit effects
57 | 0 | 2 | 0 | Create second map | 34 | Game | World | Levels | The game is made up of multiple maps which are each a level
58 | 0 | 2 | 0 | Create third map | 34 | Game | World | Levels | The game is made up of multiple maps which are each a level
70 | 0 | 2 | 0 | Implement Room Locking | 32 | Game | Map | Map generation | Maps are room based and lock all doors on player entry until enemies are cleares
25 | < | 2 | 0 | Implement pause menu audio controls | 12 | Game | UI | Pause Menu Audio controls | Lowering and raising of the audio can be done through pause menu
26 | / | 1 | 1 | Implement a HUD that shows health, ammo, and current weapon | 13 | Game | UI | HUD | There is a HUD that shows health, ammo, and current weapon
55 | > | 2 | 0 | Create multiple map integration | 34 | Game | World | Levels | The game is made up of multiple maps which are each a level
2 | > | 1 | 0 | Implement loading screen text and background | 2 | Loading Screen | Assets | Loading text/background | Loading screen has a background and loading screen text
69 | */ | 2 | 3 | Find a different sprite sheet/ remove hands from current sprite sheet | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
75 | */ | 6 | 3 | Work with Dhi to implement art assets | 36 | Polish | Polish | Polish | Polish
|  | 40 | 7
Final Deliverable | 2020-07-21
Task ID | Status | Estimate | Actual | Task | Feature ID | Game State | Area | Features | Description
|  | 0 | 0

## Journal
| Status Codes | Status meaning |  |  | Status Tags | Tag meaning
| O | Not Started |  |  | * | Not originally planned
| I | In Progress |  |  | ! | Highest priority
| X | Complete
| < | Sent to backlog
| > | Carried to next sprint
| D | Deleted
Journal
Date | Task ID | Status | Estimate | Actual | Task | Feature ID | Game State | Area | Features | Description
2020-05-26 | Q | X | Q | 3 | Deconstructed Enter The Gungeon | Q | #N/A | #N/A | #N/A | #N/A
2020-05-31 | Q | X | Q | 6 | Create features/milestones/backlog/sprints | Q | #N/A | #N/A | #N/A | #N/A
2020-05-31 | Q | X | Q | 1 | Create Overview | Q | #N/A | #N/A | #N/A | #N/A
2020-05-31 | Q | X | Q | 0.5 | Create presentation | Q | #N/A | #N/A | #N/A | #N/A
2020-06-01 | Q | I | Q | 0.5 | Change documentation to reflect mmoving data driving out of milestone 1 | Q | #N/A | #N/A | #N/A | #N/A
2020-06-01 | 65 | *X | 2 | 4 | Create Protogame as starting place | 37 | Game | Protogame | Protogame | Create Protogame as starting point
2020-06-06 | 65 | *X | 2 | 4 | Create Protogame as starting place | 37 | Game | Protogame | Protogame | Create Protogame as starting point
2020-06-07 | 66 | *X | 2 | 3 | Implement Incursion style map and tank (doesn't shoot) | 37 | Game | Protogame | Protogame | Create Protogame as starting point
2020-06-07 | 21 | X | 1 | 1 | Create camera to follow player | 9 | Game | Camera | Top down camera | Camera view is top down focusing on the player but is clamped to screen
2020-06-07 | 22 | X | 0.5 | 0.5 | Clamp camera to map dimensions | 9 | Game | Camera | Top down camera | Camera view is top down focusing on the player but is clamped to screen
2020-06-09 | 67 | *X | 4 | 5 | Refactor Testgame2D to be used as a base project | 37 | Game | Protogame | Protogame | Create Protogame as starting point
2020-06-12 | 67 | *X | 4 | 5 | Refactor Testgame2D to be used as a base project | 37 | Game | Protogame | Protogame | Create Protogame as starting point
2020-06-13 | 61 | *X | 1 | 0.5 | Create Prototype player | 20 | Game | Player | Player Character | The Player character is derived from actor with a player controller
2020-06-13 | 62 | *X | 1 | 1 | Create prototype gun | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
2020-06-13 | 63 | *X | 1 | 1 | Create Prototype bullets/firing | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
2020-06-13 | 64 | *X | 1 | 1 | Create simple Enemy character with functions to shoot | 27 | Game | Enemies | Enemy characters | Enemies are actors that may be data driven. They have on hit and on death effects to drop loot
2020-06-13 | 11 | X | 1 | 0.5 | Integrate Weapons with bullets | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
2020-06-13 | 12 | X | 1.5 | 0.5 | Integrate Weapon with actors | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
2020-06-13 | 18 | X | 1 | 1 | Implement bullet collisions | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
2020-06-13 | 19 | X | 1 | 0.5 | Find/implement basic bullet asset | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
2020-06-13 | 30 | X | 1 | 1 | Implement Actor physics with collisions of enemies and obstacles | 17 | Game | Actors | Physics | Physics like actor radius is data driven and says what the actor will collide with
2020-06-13 | 37 | X | 1 | 0.25 | Add movement controls (WASD) | 21 | Game | Player Controller | Movement | Player moves with WASD or controller left joystick
2020-06-13 | 38 | X | 1 | 0.25 | Add shooting controls (LMB) | 22 | Game | Player Controller | Shooting | Player shoots with left mouse button or controller right button
2020-06-13 | 39 | X | 1 | 0.25 | Add aiming controls (Mouse) | 23 | Game | Player Controller | Aiming | Player aims with mouse or controller right joystick
2020-06-13 | 44 | X | 2 | 0.5 | Create simple enemy controller to run at player and shoot | 28 | Game | Enemy Controller | Enemy AI Controller | Enemies have a data driven controller where they will wander until the player is spotted before chasing and shooting
2020-06-13 | 54 | X | 5 | 2.5 | Integrate map with actors and check collisions | 33 | Game | Map | Map makeup | Maps are tile based with tile definitions determining what/who they block or not block
2020-06-13 | 31 | X | 1 | 1.5 | Have weapons face actor direction moving in a circular motion around player radius | 18 | Game | Actors | Weapons | Game keeps track of current weapon and uses the weapon definitions to know the stats
2020-06-13 | 32 | X | 1 | 0.5 | Have weapons behind player at top of screen and in front of player at bottom of screen | 18 | Game | Actors | Weapons | Game keeps track of current weapon and uses the weapon definitions to know the stats
2020-06-14 | 1 | X | 1 | 1 | Implement loading state and loading functions | 1 | Loading Screen | Function | Load data | Loads game assets
2020-06-14 | 3 | X | 0.5 | 1 | Add Attract Screen functionality (space or lmb to start game) | 3 | Main Menu | Function | Buttons | Start game, Exit Game buttons to start or exit the game
2020-06-14 | Q | X | Q | 2 | Plan Milestone 2 | Q | #N/A | #N/A | #N/A | #N/A
2020-06-14 | Q | X | Q | 1 | Create presentation | Q | #N/A | #N/A | #N/A | #N/A
2020-06-20 | 8 | X | 1.5 | 2 | Create Weapon Definition | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
2020-06-20 | 9 | X | 1 | 1 | Implement shooting using weapon definition | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
2020-06-21 | 41 | X | 1 | 1 | Add changing weapons to controller class | 25 | Game | Player Controller | Changing weapons | Player can change weapons with Q/E keys or controller Y button
2020-06-21 | 13 | X | 1 | 0.5 | Find/implement first 2 weapon assets (pistol/shotgun) | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
2020-06-21 | 17 | X | 1.5 | 1.5 | Create Bullet Definition | 8 | Game | Weapons | Bullets | Bullets may be data driven with damage, visuals, VFX, and SFX
2020-06-21 | 15 | X | 1 | 0.5 | Find/implement laser gun | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
2020-06-22 | 14 | X | 1.5 | 0.5 | Find/implement machine gun and flamethrower | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
2020-06-22 | 16 | X | 1 | 0.5 | Find/implement rocket launcher | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
2020-06-23 | 23 | X | 1 | 1 | Implement screen shake | 10 | Game | Camera | Screen shake | Camera has screen shaking for for big damage taken
2020-06-23 | 68 | *X | 2 | 4 | Clean up weapon rendering | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
2020-06-23 | 69 | */ | 2 | 3 | Find a different sprite sheet/ remove hands from current sprite sheet | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
2020-06-27 | 40 | X | 1 | 1 | Add dodging to controller class | 24 | Game | Player Controller | Dodging | Player can dodge with space key or controller B button
2020-06-27 | 50 | X | 1 | 0.5 | Build Datadriven map from image file | 31 | Game | Map | Map editor | Maps are data driven and use an image with pixels determining what's on the terrain
2020-06-27 | 42 | X | 1 | 1 | Add interacting/picking up loot to controller | 26 | Game | Player Controller | Interact/pick up loot | Player can pick up weapons/interact with F key or controller A button
2020-06-27 | 51 | X | 2 | 2 | Implement enemy spawning | 32 | Game | Map | Map generation | Maps are room based and lock all doors on player entry until enemies are cleares
2020-06-27 | 49 | X | 1 | 1 | Create loot capabilities in Actor definition | 30 | Game | Actors | Loot | Loot can be dropped from enemies for example weapons, and can be picked up
2020-06-27 | 69 | */ | 2 | 3 | Find a different sprite sheet/ remove hands from current sprite sheet | 7 | Game | Weapons | Weapons | Weapons may be data driven with Weapon visual, VFX, and SFX
2020-06-27 | 75 | */ | 6 | 3 | Work with Dhi to implement art assets | 36 | Polish | Polish | Polish | Polish
2020-06-28 | 46 | X | 3 | 3.5 | Create first boss using enemies as a base. They will be enemies with bigger hitbox and multiple attacks | 29 | Game | Enemy | Boss | Bosses are enemies with a heavier data driven controller for larger attack animations and on hit effects
2020-06-28 | 26 | / | 1 | 1 | Implement a HUD that shows health, ammo, and current weapon | 13 | Game | UI | HUD | There is a HUD that shows health, ammo, and current weapon