## Features
Feature Id | Phase | Area | Features | Description
1 | Prototype | Game | Base Project | Base Project to build all future table top ai games off of
2 | Prototype | Game | Build Tic Tac Toe | Tic Tac Toe will be used to learn and understand how to architect my game for easier implementation of an AI
3 | Prototype | AI | Tic Tac Toe State machine AI | Tic Tac Toe State machine will be a test opponent for MCTS
4 | Prototype | AI | Tic Tac Toe MCTS AI | Initial learning of MCTS AI using Tic Tac Toe
5 | Dominion | Game Mechanics | Base Game | 2 Player Base Dominion game is built for easy control for both a human and an AI player. It is built very efficiently to allow for massive amounts of games on multiple threads
6 | Dominion | Game Mechanics | Dominion Base Rules | Dominion has base rules for any game excluding the cards themselves. This includes Drawing
7 | Dominion | Game Mechanics | Dominion Cards | Only cards in both first and second edition are implemented. This removes many of the complicated cards and still leaves 18 possible cards out of 10 that will be in a single game
8 | Game | UI/UX | Card Dragging | Player can drag cards from hand to play
9 | Game | UI/UX | Hand | Player's current hand is shown at the bottom of the screen
10 | Game | UI/UX | Basic Game Information | During the player's turn the player's current gold amount, amount of buys available, and amount of actions available.
11 | Game | UI/UX | Grey out invalid cards | Cards that can't be played are greyed out or shown as invalid plays
12 | Game | UI/UX | Go to Next Phase/End Turn | There is a button to move to the next phase and end turn
13 | Game | UI/UX | Opponents turns move conveyance | Opponents plays are highlighted to show what they did
14 | Game | AI | Big Money State Machine | A state machine using the Big money algorithm where only the highest money value is bought until the average money density reaches enough to buy a province every turn
15 | Game | AI | Single Witch State Machine | A state machine using the Single Witch algorithm where Big Money is used except for getting a single witch as soon as possible
16 | Game | AI | MCTS | MCTS is implemented with exposed variables for tweaking the algorithm like selection method and Exploration parameter
17 | Game | AI | MCTS Move Score | There is a toggleable UI element to show the Ais current move score for each buy
18 | Game | Analysis | Game Simulation | Dominion games can go into simulation mode where the games go as fast as possible and aren't renderered on screen.
19 | Game | Main Menu | Buttons | Game has buttons for Play game, Quit game, and setup simulation
20 | Game | Analysis | Simulation controls | Simulation controls for numer of simulations, which AIs play against each other, variations for MCTS, how long to let MCTS think, etc.
21 | Game | Analysis | Results Output Log | The results of the simulations are outputted both on screen and out to a text file
22 | Game | Play Game Menu | Start Game | There is a start game button on the play game menu
23 | Game | Play Game Menu | Random cards or chosen cards | You can choose whether the card piles are random or specified from a given list
24 | Results | Results | MCTS vs Single Witch and Big Money analysis | The results between MCTS and Single Witch/Big Money are written up to show how well (or poorly) MCTS did with the different variations
Simple Cards To Implement (no extra choices) | Difficult cards to implement ( more choices )
Supply cards | Cellar
Moat | Chapel
Village | Militia
Workshop | MoneyLender
Bureaucrat | Remodel
Gardens | Throne Room
Smith | Chancellor
Council Room | Feast
Festival | Spy
Laboratory | Thief
Library | Adventurer
Market
Mine
Witch
Woodcutter

## Milestones
Milestones | Feature ID | Phase | Area | Features | Description
Milestone 1 | 1 | Prototype | Game | Base Project | Base Project to build all future table top ai games off of
Milestone 1 | 2 | Prototype | Game | Build Tic Tac Toe | Tic Tac Toe will be used to learn and understand how to architect my game for easier implementation of an AI
Milestone 1 | 3 | Prototype | AI | Tic Tac Toe State machine AI | Tic Tac Toe State machine will be a test opponent for MCTS
Milestone 1 | 4 | Prototype | AI | Tic Tac Toe MCTS AI | Initial learning of MCTS AI using Tic Tac Toe
Milestone 2 | 5 | Dominion | Game Mechanics | Base Game | 2 Player Base Dominion game is built for easy control for both a human and an AI player. It is built very efficiently to allow for massive amounts of games on multiple threads
Milestone 2 | 6 | Dominion | Game Mechanics | Dominion Base Rules | Dominion has base rules for any game excluding the cards themselves. This includes Drawing
Milestone 2 | 7 | Dominion | Game Mechanics | Dominion Cards | Only cards in both first and second edition are implemented. This removes many of the complicated cards and still leaves 18 possible cards out of 10 that will be in a single game
Milestone 3 | 8 | Game | UI/UX | Card Dragging | Player can drag cards from hand to play
Milestone 3 | 9 | Game | UI/UX | Hand | Player's current hand is shown at the bottom of the screen
Milestone 3 | 10 | Game | UI/UX | Basic Game Information | During the player's turn the player's current gold amount, amount of buys available, and amount of actions available.
Milestone 3 | 14 | Game | AI | Big Money State Machine | A state machine using the Big money algorithm where only the highest money value is bought until the average money density reaches enough to buy a province every turn
Milestone 3 | 16 | Game | AI | MCTS | MCTS is implemented with exposed variables for tweaking the algorithm like selection method and Exploration parameter
Milestone 4 | 11 | Game | UI/UX | Grey out invalid cards | Cards that can't be played are greyed out or shown as invalid plays
Milestone 4 | 12 | Game | UI/UX | Go to Next Phase/End Turn | There is a button to move to the next phase and end turn
Milestone 4 | 13 | Game | UI/UX | Opponents turns move conveyance | Opponents plays are highlighted to show what they did
Milestone 4 | 15 | Game | AI | Single Witch State Machine | A state machine using the Single Witch algorithm where Big Money is used except for getting a single witch as soon as possible
Milestone 4 | 16 | Game | AI | MCTS | MCTS is implemented with exposed variables for tweaking the algorithm like selection method and Exploration parameter
Milestone 5 | 17 | Game | AI | MCTS Move Score | There is a toggleable UI element to show the Ais current move score for each buy
Milestone 5 | 19 | Game | Main Menu | Buttons | Game has buttons for Play game, Quit game, and setup simulation
Milestone 5 | 22 | Game | Play Game Menu | Start Game | There is a start game button on the play game menu
Milestone 5 | 16 | Game | AI | MCTS | MCTS is implemented with exposed variables for tweaking the algorithm like selection method and Exploration parameter
Milestone 6 | 18 | Game | Analysis | Game Simulation | Dominion games can go into simulation mode where the games go as fast as possible and aren't renderered on screen.
Milestone 6 | 20 | Game | Analysis | Simulation controls | Simulation controls for numer of simulations, which AIs play against each other, variations for MCTS, how long to let MCTS think, etc.
Milestone 6 | 21 | Game | Analysis | Results Output Log | The results of the simulations are outputted both on screen and out to a text file
Milestone 6 | 23 | Game | Play Game Menu | Random cards or chosen cards | You can choose whether the card piles are random or specified from a given list
Milestone 6 | 16 | Game | AI | MCTS | MCTS is implemented with exposed variables for tweaking the algorithm like selection method and Exploration parameter
Milestone 7 | 24 | Results | Results | MCTS vs Single Witch and Big Money analysis | The results between MCTS and Single Witch/Big Money are written up to show how well (or poorly) MCTS did with the different variations